## Sheet1
Task | Time needed
Villager needs system and agent actions | 8 days
Create basic objects | 4 hours
Create Storeroom, with water and food | 1 hour
Create House, with ability to hold villager | 1 hour
Create Villager, with hunger thirst and energy | 1 hour
Needs system for villagers | 2 days
¦ Hunger decreasing over time | 2 hours
¦ Hunger Replenishing after eating | 2 hours
¦ Thirst decreasing over time | 2 hours
¦ Thirst replenishing after drinking | 2 hours
¦ Energy decreasing over time | 2 hours
¦ Energy replenishing while sleeping | 2 hours
¦ Villager dying when a need reaches zero | 2 hours
Actions Villagers can make | 1 day
¦ Move to location | 2 hours
¦ pick up resource (food, water, etc.) | 2 hours
¦ Consume Food/Water | 2 hours
¦ Sleep | 2 hours
Agent system | 4 days
¦ Create system for checking needs | 4 hours
¦ Allow villagers to know how to eat, drink and sleep | 4 hours
¦ Create prioritisation for which need to attend to | 6 hours
¦ Make agent action on highest priority action | 6 hours
Village building system | 8 days
Create Buildings | 3 days
¦ Create Farm that produces food | 4 hours
¦ Create well that produces water | 2 hours
¦ Create mine that produces stone | 4 hours
¦ Create Forrester Building that produces Wood | 2 hours
¦ Create system that allows building placement in the world | 6 hours
Create villager building jobs | 3 days
¦ Create job list that is visible by agents | 4 hours
¦ Allow Agents to select a job and add it to priority list | 8 hours
¦ Make agents create buildings based on job selected | 4 hours
¦ Have buildings cost Stone and Wood to build | 4 hours
Resource production and storage | 1 day
¦ Add stone and Wood to storehouse storage | 2 hours
¦ Require resources to be moved to storehouse before they can be used | 4 hours
¦ Allow villagers to carry resources | 2 hours
Village growth and interactions | 1 day
¦ Have additional villagers spawn when there is a surplus of food and more houses than villagers | 4 hours
¦ have production buildings only produce resources when worked by a villager | 4 hours
Finalisations | 8 days
Testing | 2 days
Write documentation | 2 days
Write final report | 4 days
Total time | 24 days

## Sheet2
| Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
| 2018-03-03 | 2018-03-04 | 2018-03-05 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-24 | 2018-03-25 | 2018-03-26 | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04
Villager needs system and agent actions
Create basic objects
Create Storeroom, with water and food
Create House, with ability to hold villager
Create Villager, with hunger thirst and energy
Needs system for villagers
¦ Hunger decreasing over time
¦ Hunger Replenishing after eating
¦ Thirst decreasing over time
¦ Thirst replenishing after drinking
¦ Energy decreasing over time
¦ Energy replenishing while sleeping
¦ Villager dying when a need reaches zero
Actions Villagers can make
¦ Move to location
¦ pick up resource (food, water, etc.)
¦ Consume Food/Water
¦ Sleep
Agent system
¦ Create system for checking needs
¦ Allow villagers to know how to eat, drink and sleep
¦ Create prioritisation for which need to attend to
¦ Make agent action on highest priority action
Village building system
Create Buildings
¦ Create Farm that produces food
¦ Create well that produces water
¦ Create mine that produces stone
¦ Create Forrester Building that produces Wood
¦ Create system that allows building placement in the world
Create villager building jobs
¦ Create job list that is visible by agents
¦ Allow Agents to select a job and add it to priority list
¦ Make agents create buildings based on job selected
¦ Have buildings cost Stone and Wood to build
Resource production and storage
¦ Add stone and Wood to storehouse storage
¦ Require resources to be moved to storehouse before they can be used
¦ Allow villagers to carry resources
Village growth and interactions
¦ Have additional villagers spawn when there is a surplus of food and more houses than villagers
¦ have production buildings only produce resources when worked by a villager
Finalisations
Testing
Write documentation
Write final report